## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 97) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23
|  |  |  | 2020-02-25: 97; 2020-02-26: 95; 2020-02-27: 93; 2020-02-28: 91; 2020-02-29: 89; 2020-03-01: 87; 2020-03-02: 85; 2020-03-03: 83; 2020-03-04: 81; 2020-03-05: 79; 2020-03-06: 77; 2020-03-07: 75; 2020-03-08: 73; 2020-03-09: 71 | Ideal Burndown
|  |  | 97 | 2020-02-25: 2; 2020-02-26: 2; 2020-02-27: 2; 2020-02-28: 2; 2020-02-29: 2; 2020-03-01: 2; 2020-03-02: 2; 2020-03-03: 2; 2020-03-04: 2; 2020-03-05: 2; 2020-03-06: 2; 2020-03-07: 2; 2020-03-08: 2; 2020-03-09: 2 | Remaining Hrs (Total)
Enable all users to place book in shopping cart | Requirements Gathering | All team members | 30 | 2020-02-25: 2; 2020-02-26: 2; 2020-02-27: 2; 2020-02-28: 2; 2020-02-29: 2; 2020-03-01: 2; 2020-03-02: 2; 2020-03-03: 2; 2020-03-04: 2; 2020-03-05: 2; 2020-03-06: 2; 2020-03-07: 2; 2020-03-08: 2; 2020-03-09: 2
| Writing User Story | Manasa | 30
| Architecture Diagram | Sneha | 20
| Deciding Technology Stack | All team members | 2
| Setting up server | Ambika | 5
| Researching on AWS resources | All team members | 10
| Front End Login Development | Ambika | 5 | bar: 2020-03-10 to 2020-03-14
| Design - User Module | Sneha | 5 | bar: 2020-03-10 to 2020-03-14
| Design - Admin Module | Manasa | 5 | bar: 2020-03-10 to 2020-03-14
| DB Modeling - Discussion | All team members | 3 | 2020-03-22: 3
| DB Setup | Sneha
| Front End Design Discussion | All team members
| User Registration | Ambika
| User Login | Ambika
| Search and Browse rental location and vehicles | Sneha
| My reservation tab with option to Cancel and Return | Manasa
| Vehicle reservation and validation | Sneha
| Condition and Comment for returned vehicle | Manasa
| My membership tab with option to terminate | Ambika
| For Admin, terminate user membership | Manasa
For Admin, Add rental locations | Add and update database using queries for individual vehicles and rental locations. | Manasa
For Admin, Add vehicles and vehicle Types
| User Authentication n authorization | Ambika
| Architecture Diagram and documentation | Manasa
| AWS with load balancer | Sneha
| Login for user and admin | Ambika
Team:
Manasa Hari | 10 hours / Week
Ambika Na | 10 hours / Week
Sneha Patil | 10 hours / Week
Total Available Hours During Sprint: | 97