## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 97) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23
|  |  |  | 2020-02-25: 97; 2020-02-26: 95; 2020-02-27: 93; 2020-02-28: 91; 2020-02-29: 89; 2020-03-01: 87; 2020-03-02: 85; 2020-03-03: 83; 2020-03-04: 81; 2020-03-05: 79; 2020-03-06: 77; 2020-03-07: 75; 2020-03-08: 73; 2020-03-09: 71 | Ideal Burndown
|  |  | 97 | 2020-02-25: 2; 2020-02-26: 2; 2020-02-27: 2; 2020-02-28: 2; 2020-02-29: 2; 2020-03-01: 2; 2020-03-02: 2; 2020-03-03: 2; 2020-03-04: 2; 2020-03-05: 2; 2020-03-06: 2; 2020-03-07: 2; 2020-03-08: 2; 2020-03-09: 2 | Remaining Hrs (Total)
Enable all users to place book in shopping cart | Requirements Gathering | All team members | 30 | 2020-02-25: 2; 2020-02-26: 2; 2020-02-27: 2; 2020-02-28: 2; 2020-02-29: 2; 2020-03-01: 2; 2020-03-02: 2; 2020-03-03: 2; 2020-03-04: 2; 2020-03-05: 2; 2020-03-06: 2; 2020-03-07: 2; 2020-03-08: 2; 2020-03-09: 2
| Writing User Story | Manasa | 30
| Architecture Diagram | Sneha | 20
| Deciding Technology Stack | All team members | 2
| Setting up server | Ambika | 5
| Researching on AWS resources | All team members | 10
| Front End Login Development | Ambika | 5 | bar: 2020-03-10 to 2020-03-14
| Design - User Module | Sneha | 5 | bar: 2020-03-10 to 2020-03-14
| Design - Admin Module | Manasa | 5 | bar: 2020-03-10 to 2020-03-14
| DB Modeling - Discussion | All team members | 3 | 2020-03-22: 3
| DB Setup | Sneha
| Front End Design Discussion | All team members
| User Registration | Ambika
| User Login | Ambika
| Search and Browse rental location and vehicles | Sneha
| My reservation tab with option to Cancel and Return | Manasa
Vehicle reservation and validation
Condition and Comment for returned vehicle
My membership tab with option to terminate
For Admin, terminate user membership
For Admin, Add rental locations
For Admin, Add vehicles and vehicle Types
Team:
Manasa Hari | 10 hours / Week
Ambika Na | 10 hours / Week
Sneha Patil | 10 hours / Week
Total Available Hours During Sprint: | 97